## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
I catch CoViD | 3 | 40 | 120 | 2021-01-14 | Mitigated | M | learned instructor has extension possible
My gecko is not working | 3 | 20 | 60 | 2021-01-14 | Resolved | R | Test it. If mine not working, contact instructor
Capsense bug affects gameplay | 100 | 40 | 4000 | 2022-03-11 |  | A | Game shouldn't idle for too long. No workaround.
Screen bug affects gameplay | 100 | 13 | 1300 | 2022-03-11 | Resolved | R | Can borrow Lena's PG12
Capstone scheduling conflict | 20 | 3 | 60 | 2022-03-11 |  | O | Contact instruction team after examining schedule.
New medicine side effect (Emotional Blunting) | 20 | 20 | 400 | 2022-04-01 |  | O | Reach out to doctor/ Find someone to work with
New medicine side effect (Insomnia) | 40 | 3 | 120 | 2022-04-01 |  | O | Reach out to doctor/ Work at night
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100